## Burnup
Instructions Get a feel for the template by familiarizing yourself with the example below. Then clear out the example by deleting only the values in cells A4:D33. At the end of each Sprint, fill in one row from columns A - D.
Sprint # | Sprint Start Date | Points Complete in Sprint | Total Scope Known at end of Sprint
1 | 2021-09-13 | 5 | 200
2 | 2021-09-20 | 15 | 250
3 | 2021-09-27 | 25 | 300
4 | 2021-10-04 | 35 | 220
5 | 2021-10-11 | 50 | 370
6 | 2021-10-18 | 35 | 420
7 | 2021-10-25 | 25 | 400
8 | 2021-11-01 | 25 | 430
9 | 2021-11-08 | 10 | 360
10 | 2021-11-15 | 10 | 410
11 | 2021-11-22 | 10 | 375
12 | 2021-11-29 | 10 | 390
13 | 2021-12-06 | 10 | 380
14 | 2021-12-13
15 | 2021-12-20
16 | 2021-12-27
17 | 2022-01-03
18 | 2022-01-10
19 | 2022-01-17
20 | 2022-01-24
21 | 2022-01-31
22 | 2022-02-07
23 | 2022-02-14
24 | 2022-02-21
25 | 2022-02-28
26 | 2022-03-07
27 | 2022-03-14
28 | 2022-03-21
29 | 2022-03-28
30 | 2022-04-04
How to read the burnup chart The burnup chart above tracks progress towards a goal. The blue line tells the story of scope changing as more is learned about the product. This line rises when new user stories are added to the backlog and falls when user stories are dropped from the backlog. The red bars display the cumulative total of story points completed and are used to tell the story of team velocity. When the points completed (red bar) meet the blue scope line, the goal being tracked has been met. When the top of the red bars forms a line curving up (sprints 1-5), the team’s velocity is accelerating. When the top of the red bars forms a line curving down (sprints 5-9), the team’s velocity is decelerating. When the top of the red bars forms a straight line (sprints 9-13), the team’s velocity has stabilized. Stable velocity is a sign of a mature team and is helpful for planning. The yellow line is a forecast of when the team will meet their goal if they were to continue to progress at the pace of their average three-sprint velocity. The black line points to the forecasted completion date and is where the yellow forecast line crosses the blue scope line. In the example below, the forecasted completion date is at the end of sprint 24, which is 02/28/2022. The forecasted date is not a commitment, it is the most likely completion date given the information available and is expected to change every sprint. The forecasted date often shifts by a wide margin at the start of an initiative and stabilizes as the team nears completion.
The Ultimate Burn-Up Chart Template by Superheroes Academy is licensed under a Creative Commons Attribution-ShareAlike 4.0 International License.
Note on D3: ====== ID#AAAAcRy3k4M (2022-06-30 21:03:50) This includes all story points already completed and yet to be completed that are known at the end of the sprint. Points deleted from the backlog because the features won't be implemented do not count towards the total.

## Formulas
Don't change these values. They are generated automatically as data is entered into the table on the first sheet labelled, "Burnup".
Sprint Label | Total Points Complete | Projected Points | Total Scope Known at end of each Sprint | Average Velocity | Goal Complete
1 - 09/13/2021 | 5 | #N/A | 200 | 5 | #N/A
2 - 09/20/2021 | 20 | #N/A | 250 | 10 | #N/A
3 - 09/27/2021 | 45 | #N/A | 300 | 15 | #N/A
4 - 10/04/2021 | 80 | #N/A | 220 | 25 | #N/A
5 - 10/11/2021 | 130 | #N/A | 370 | 36.6667 | #N/A
6 - 10/18/2021 | 165 | #N/A | 420 | 40 | #N/A
7 - 10/25/2021 | 190 | #N/A | 400 | 36.6667 | #N/A
8 - 11/01/2021 | 215 | #N/A | 430 | 28.3333 | #N/A
9 - 11/08/2021 | 225 | #N/A | 360 | 20 | #N/A
10 - 11/15/2021 | 235 | #N/A | 410 | 15 | #N/A
11 - 11/22/2021 | 245 | #N/A | 375 | 10 | #N/A
12 - 11/29/2021 | 255 | #N/A | 390 | 10 | #N/A
13 - 12/06/2021 | 265 | #N/A | 380 | 10 | #N/A
14 - 12/13/2021 |  | 275 | 380 |  | #N/A
15 - 12/20/2021 |  | 285 | 380 |  | #N/A
16 - 12/27/2021 |  | 295 | 380 |  | #N/A
17 - 01/03/2022 |  | 305 | 380 |  | #N/A
18 - 01/10/2022 |  | 315 | 380 |  | #N/A
19 - 01/17/2022 |  | 325 | 380 |  | #N/A
20 - 01/24/2022 |  | 335 | 380 |  | #N/A
21 - 01/31/2022 |  | 345 | 380 |  | #N/A
22 - 02/07/2022 |  | 355 | 380 |  | #N/A
23 - 02/14/2022 |  | 365 | 380 |  | #N/A
24 - 02/21/2022 |  | 375 | 380 |  | #N/A
25 - 02/28/2022 |  | 385 | 380 |  | 385
26 - 03/07/2022 |  | 395 | 380 |  | #N/A
27 - 03/14/2022 |  | 405 | 380 |  | #N/A
28 - 03/21/2022 |  | 415 | 380 |  | #N/A
29 - 03/28/2022 |  | 425 | 380 |  | #N/A
30 - 04/04/2022 |  | 435 | 380 |  | #N/A
Note on D2: This includes all points already completed and yet to be completed. Points deleted from the backlog because the features won't be implemented do not count towards the total.